## WBS
WBS Number | Task Name | WBS Description | Must Start by Date | Must End by Date | Task Level of Effort (in hours) | Task Duration (in days) | Predecessor (Finish-to-Start Dependency) (comma separated) | Resource Name(s) | Author (of Item for follow-on questions)
1 | Develop the Database | The Database will hold all information about user credentials and all their content that has been posted on the website. | 2021-08-19 | 2021-08-19 | 4 hours | <1 day | Normalize Database |  | Arjun Prashant
1.1 | Develop the Database Structure | The database will include partition/collections, these will be user, user blogs etc. Each user blog will have a unique id that'll connect it to the user. |  |  |  |  | Create a Database and make collections like users, blogs and posts.
2 | Design the Sign Up Page | The Sign Up page is developed as intended by the stakeholders/us. | 2021-08-22 | 2021-08-27 | 20-30 hours | 5 days | Data Entry |  | Krishnaswaroop Varati
2.1 | Accept User data (Email & Password) | Inclusion of data entry forms to get Email and Password of user |  |  |  |  | Data Entry for user email and password and check validity of email
2.1.1 | Generate User ID and hash the password | Encrytion of Password. |  |  |  |  | Use Bcrypt library for hashing password and uuid for user ID
2.1.2 | Store Email and Password in database. | Storing of Encrypted Password in database. |  |  |  |  | Set ID as User ID
3 | Design Login Page | The Login page is developed as intended by the stakeholders/us. | 2021-08-27 | 2021-09-02 | 20-30 hours | 5 days |  |  | Ansh Goel
3.1 | Accept Email and Password | Inclusion of data entry forms to get Email and Password of user |  |  |  |  | Use post request form
3.1.1 | Check validity of given password | Hash given password and check against the password in database. |  |  |  |  | Bcrypt & MongoDB query
4 | Create Blog Page | The Create Blog Page is developed as intended by the stakeholder/us. | 2021-09-02 | 2021-09-10 | 30-35 hours | 8 days |  |  | Krishnaswaroop Varati
4.1 | Create form to accept Blog title and Description. | Inclusion of data entry forms to get Blog Title and Blog Description. |  |  |  |  | HTML CSS
4.2 | Generate a blog ID and its corresponding user ID and add it to the Database. | [5 empty] | uuid for blog ID and addition to database
5 | Create Post Page | The Post Page is developed as intended by the stakeholder/us. | 2021-09-10 | 2021-09-17 | 30-35 hours | 7 days |  |  | Arjun Prashant
5.1 | Create form to accept Post title and Description. | Inclusion of data entry forms to get Post title and description |  |  |  |  | HTML CSS
5.2 | Generate a post ID and its corresponding blog ID and add it to the Database. | [5 empty] | uuid for post ID and addition to Database.
6 | Create My Blogs page | The My Blog Page is developed as intended by the stakeholder/us. | 2021-09-17 | 2021-09-23 | 25-30 hours | 6 days |  |  | Ansh Goel
6.1 | Fetch list of blogs created by user using user ID | Using unique IDs of user and corresponding posts the list of all blogs belonging to a user is displayed |  |  |  |  | MongoDB query
6.1.1 | Fetch list of post under each blog | All posts under that blog is displayed |  |  |  |  | MongoDB query
6.2 | Display the Blogs and the posts under them in a systematic way. | [5 empty] | Purchase and install all required softwares' licenses
7 | Test the Web Application | We run and debug each component in the web interface to make sure it runs smoothly | 2021-09-23 | 2021-10-15 | 40 hours | 24 days | Use linter check and pytest library for tests |  | Arjun Prashant, Ansh Goel, Krishnaswaroop Varati
8 | Deploy the Web Interface | The website is hosted on Heroku | 2021-10-16 | 2021-10-16 | 2 hours | <1 day | Requirements.txt and Procfile